Power
Supply
Card
Battery
Card
1U Structure
Solar Panels
6 Solar
Panels
Power bus
70 cm
Antenna
2 m
Antenna
Science
Payloads
IHU
Card
Passive
Magnetic Attitude
Control
Telemetry
RF TxRx
Card
Fox-Plus A Block Diagram

---
Minimum Viable Product
Commercial 1U frame (ISISpace)
Commercial EPS (ISISpace)
LTM
C&DH
TX/RX
RT-IHU (nice to have)
Passive attitude control (???)
Fox-Plus-A

---
ICR EOL Replacement
ASCENT Leadership, Fox-Plus Leadership, and/or Volunteer Onboarding (share the fun!)
Fox-Plus A Launch Options Trade Study
Reaction Wheel Driver and Software
RT-IHU Board Checkout-Out Test Procedure
Golf-Tee Test Procedures
Thruster Working Group
Physical Golf-TEE Model
Job Jar

---
and
FOX+
What’s Happening?

---
- Update CONOPS/PDR – Don Mills
- Update SRS – Geoffrey Gentile
- Radiation Research – Carl Wick
GOLF-TEE

---
- Objective
  - Advance systems engineering tasks
- Team
  - Mike Moore
- Current Activity
  - Frequency Coordination
  - Fox-Plus PDR
Fox-Plus Systems Engineering

---
  - Model the Fox-Plus stack
  - Thomas Wu
  - Duane Moberg
  - Model the Fox-Plus stack with LTM and ISISpace EPS (Thomas, Duane)
  - Ordered with 5 – 6 month lead time: (Jonathan) – Our money finally made it to their bank!!!
    - 2 x 1U frame
    - 2 x assembly jig
    - 2 x EPS
    - 1 x Ground Power
    - 2 x Deployable Antenna
Fox-Plus Structure

---
  - Order a whole stack of LTMs
  - Leandra MacLennan
  - Arun Kumar
  - Get me some LTM sets for development (Leandra)
    - Starting on LIHU BoM
  - ICR Assembly (Arun Kumar)
    - Jonathan has all the parts and needs to kit them for Arun
  - RX/TX assembly
    - Assembling two more and dealing with EOL (Dan)
Fox-Plus C&DH (aka IHU) Hardware

---
  - Develop SSTV transmitter
  - Will Brozovic
  - Reviewing SSTV (Will)
ASCENT SSTV TX

---
  - Develop SDR for Golf
  - Rich Gopstein
  - Ray Roberge
  - Build of Linux for ZedBoard (Rich)
  - Design radio board (Ray & Rich)
ASCENT SDR Plan B

---
  - Develop 3U space frame
  - Tom Karnauskas
  - Design 3U frame
    - Model cards in candidate frame (Tom)
ASCENT Structure

---
  - Develop multi-channel FM Transponder
  - Andrew Robinson
  - Joseph DiVerdi
  - Survey open source designs (Andrew)
ASCENT Multi-Chan FM

---
- Current Activities
  - Layout RT-IHU V1.2 (Cameron)
  - Reliable Debug Board (Chris)
  - Assemble RT-IHU Payload
  - Cameron Castillo
  - Chris Grill
RT-IHU

---
- Current Activities
  - AMCOM (Heimir)
  - Linux build (I think)
  - Heimir Sverrisson
AMCOM

---
  - Develop digital packet communication payload
- Team (typically on this call)
  - Jim McCullers
ASCENT PACSAT

---
  - Develop deployable solar panels
  - Duane Moberg
  - Design solar panel and hinge solution
    - Ordered prototype components
ASCENT Deployable Solar Panels

---
  - Identify AX5043 Replacement
  - Identify LNA Replacement
  - Dave Hartrum
ASCENT RF Chip Trade Study

---
  - Identify environmental sensor for CubeSat Simulator use by KidzSat.
  - Joseph DiVerdi
ASCENT Environmental Sensors