## Sheet1
Fox-Plus Compliance and Testing Requirements and Documents
Last update:	04/17/23
This spreadsheet is intended to organize compliance and testing documents for Fox-Plus with descriptions

Checklist
Task Areas	Comments
	Compliance Task Areas / Examples “Launch Compliance Task Areas”
Outgassing
Venting Analysis
Frequency Coordination
Mass Properties
Electrical Report
Orbital Debris Assessment Report
Materials List
Mission Readiness Review
Environmental Test Plan
CubeSat Acceptance Checklist (CAC)	dimensional verification
Missle Sys Prelaunch Safety Package	often required on USSF launches
Certification of Flight Worthiness
NOAA Imaging Approval Licensing
Battery Report
Vibration & Shock Test Report
Transmitter Survey
Day-in-the-Life (DITL) Test / Report
Thermal Vacuum – Bakeout Test / Report
Compliance Letter
Payload Readiness Review	often required on USSF launches

Compliance
Compliance Task Area	Document	Source Location(s)	Comments
	NASA Standards and Test Documents	Note: these docs are only a sampling of what’s available on svn
CubeSat Acceptance Checklist (CAC)	cubesatdesignspecificationrev14_12022-02-09.pdf	Svn > Golf-Tee\ Mechanical \ reference \ NASA
CubeSat Acceptance Checklist (CAC)	1U++ CubeSat Checklist	Svn > Golf-Tee\ Mechanical \ reference \ NASA
Environmental Test Plan	NASA HDBK 7008	Svn > Golf-Tee\ Mechanical \ reference \ NASA	Spacecraft Dynamic Environments Testing
Outgassing	NASA STD 6001B	Svn > Golf-Tee\ Mechanical \ reference \ NASA	Flamability, Offgassing Compatability & Test
Environmental Test Plan	NASA ENV GSFC-STD-7000B (2021).pdf	Svn > Golf-Tee\ Mechanical \ reference \ NASA	General Environmental Verification Standard (GEVS) for GSFC Flight Programs and Projects
Vibration & Shock Test Report	NASA STD 7001B	Svn > Golf-Tee\ Mechanical \ reference \ NASA	Payload VibroAcoustic Test Criteria
Orbital Debris Assessment Report	NASA NPR 8715	Svn > Golf-Tee\ Mechanical \ reference \ NASA	Procedural Requirements for limiting Orbital Space Debris
Frequency Coordination	NASA Spectrum Guidance for Small Sat Missions	Svn > Golf-Tee\ Mechanical \ reference \ NASA
Frequency Coordination	FCC License DA-13-445A1.pdf	Svn > Golf-Tee\ Mechanical \ reference \ NASA
Payload Readiness Review	NASA Launch Services Program.pdf	Svn > Golf-Tee\ Mechanical \ reference \ NASA
Mass Properties	NASA VCLS ELaNa XX Mass Properties.xlsx	Svn > Golf-Tee\ Mechanical \ reference \ NASA
Payload Readiness Review	2014-01-30_LSP-REQ-317_REV_B_Final.pdf	Svn > Golf-Tee\ launch	Launch Services Program Dispenser & CubeSat Requirements Doc

	Fox 1E Procedures and Actuals
Thermal Vacuum – Bakeout Test / Report	RadFxSat-2 Bakeout manual log.xlsx	svn > Fox-1E\ Test \ Launch
Thermal Vacuum – Bakeout Test / Report	RadFxSat-2 Bakeout Test Procedure.docx	svn > Fox-1E\ Test \ Launch
Mission Readiness Review	RadFxSat-2 Launch Acceptance and Approval.docx	svn > Fox-1E\ Test \ Launch
Mass Properties	RadFxSat-2 mass measurements.xlsx	svn > Fox-1E\ Test \ Launch
Mass Properties	RadFxSat-2 Mass Properties Report.docx	svn > Fox-1E\ Test \ Launch
Vibration & Shock Test Report	RadFxSat-2 Random Vibration Test Procedure.docx	svn > Fox-1E\ Test \ Launch
Vibration & Shock Test Report	RadFxSat-2 shock.xlsx	svn > Fox-1E\ Test \ Launch
Vibration & Shock Test Report	RadFxSat-2 Shock Analysis.docx	svn > Fox-1E\ Test \ Launch
Venting Analysis	RadFxSat-2 Venting.xls	svn > Fox-1E\ Test \ Launch
Venting Analysis	RadFxSat-2 Venting Analysis Report.docx	svn > Fox-1E\ Test \ Launch
Thermal Vacuum – Bakeout Test / Report	RadFXSat-2 Bakeout Test Report.docx	svn > Fox-1E\ Test \ Launch
Mission Readiness Review	RadFXSat-2 Preflight Init Procedure pre-frame.docx	svn > Fox-1E\ Test \ Launch
Vibration & Shock Test Report	RadFXSat-2 SFT Subset for post-stack testing pre-frame.docx	svn > Fox-1E\ Test \ Launch
Vibration & Shock Test Report	RadFXSat-2 Vibration Test Report.docx	svn > Fox-1E\ Test \ Launch

	ELaNa and Other
CubeSat Acceptance Checklist (CAC)	VCLS ELaNa XX CubeSat Description - RadFXSat-2.docx	svn > Fox-1E\ Test \ Launch
Materials List	Fox 1C Materials List	Svn > Golf-Tee\ Mechanical \ requirements
Payload Readiness Review	P-Pod_MKIIIRevE_UserGuide_CP_PPODUG-1.0-1_Rev1.pdf	Svn > Golf-Tee\ Mechanical \ requirements
Mass Properties	spec_dwgs_rev13cds.pdf	Svn > Golf-Tee\ Mechanical \ requirements
Radiation Testing	Fox_Radiation(Tony Monteiro).pdf
Radiation Testing	TID for CubeSat Components		Total Ionizing Dose (TID) for CS Components