Power
Supply
Card
Battery
Card
1U Structure
Solar Panels
6 Solar
Panels
Power bus
70 cm
Antenna
2 m
Antenna
Science
Payloads
IHU
Card
Passive
Magnetic Attitude
Control
Telemetry
RF TxRx
Card
Fox-Plus A Block Diagram

---
Minimum Viable Product
Commercial 1U frame (ISISpace)
Commercial EPS (ISISpace)
LTM
C&DH
TX/RX
RT-IHU (nice to have)
Passive attitude control (???)
Fox-Plus-A

---
- Douglas Quagliana
  - Welcome back!
- Arun Kumar
  - Welcome back!
  - PCB Assembly?
- Neil Heft
  - Reaction Wheel Driver
- Bill Werner
Recent Volunteers

---
ICR Assembly – Arun Kumar?
ICR EOL Replacement
Reaction Wheel Driver and Software – Neil Heft?, Carl Wick?
Fox-Plus A Launch Options Trade Study
ASCENT Leadership, Fox-Plus Leadership, and/or Volunteer Onboarding (share the fun!)
RT-IHU Board Checkout-Out Test Procedure
Golf-Tee Test Procedures
Thruster Working Group
Physical Golf-TEE Model
Job Jar

---
and
FOX+
What’s Happening?

---
- Update CONOPS/PDR – Don Mills
- Update SRS – Geoffrey Gentile (present)
- Radiation Research – Carl Wick
GOLF-TEE

---
- Objective
  - Advance systems engineering tasks
- Team
  - Mike Moore (notified)
- Current Activity
  - Frequency Coordination
  - Fox-Plus PDR
    - Jonathan action item: post ISISpace data sheets
Fox-Plus Systems Engineering

---
  - Model the Fox-Plus stack
  - Thomas Wu
  - Duane Moberg (present)
  - Need to adapt Fox boards to 1U frame (Thomas, Duane)
  - Model the Fox-Plus stack with LTM and ISISpace EPS (Thomas, Duane)
  - Ordered with 5 – 6 month lead time: (Jonathan)
    - 2 x 1U frame
    - 2 x assembly jig
    - 2 x EPS
    - 1 x Ground Power
    - 2 x Deployable Antenna
Fox-Plus Structure

---
  - Fox-Plus flight software
  - Dave McCoy (present, but silent :( )
  - Chris Grill (notified)
  - Will Brozovic (present)
  - Assemble prototype environment (Dave)
  - Bring up LTM (Chris)
Fox-Plus C&DH (aka IHU) Flight Software

---
  - Order a whole stack of LTMs
  - Leandra MacLennan (present)
  - Get me some LTM sets for development (Leandra)
    - Starting on LIHU BoM
  - Order ICR parts (Jonathan)
    - Done (almost)!
  - Order ICR boards (Jonathan)
    - Received
  - RX/TX assembly
    - Assembling two more and dealing with EOL (Dan)
Fox-Plus C&DH (aka IHU) Hardware

---
  - Develop 3U space frame
  - Tom Karnauskas (present)
  - Design 3U frame
    - Model cards in candidate frame (Tom)
ASCENT Structure

---
  - Develop multi-channel FM Transponder
  - Andrew Robinson
  - Joseph DiVerdi (present)
  - Survey open source designs (Andrew)
ASCENT Multi-Chan FM

---
  - Develop SSTV transmitter
  - Will Brozovic (present)
  - Reviewing SSTV (Will)
ASCENT SSTV TX

---
  - Develop SDR for Golf (i.e., five-and-dime)
  - Rich Gopstein (present)
  - Ray Roberge (present)
  - Build of Linux for ZedBoard (Rich)
  - Design radio board (Ray & Rich)
ASCENT SDR Plan B

---
- Current Activities
  - Flash Loader (Heimir)
    - Result is an updated flash loader to load the RT-IHU board
  - Layout RT-IHU V1.2 (Cameron)
  - Reliable Debug Board (Chris)
  - Assemble RT-IHU Payload
  - Heimir Sverrisson
  - Cameron Castillo
  - Chris Grill (notified)
RT-IHU

---
  - Develop digital packet communication payload
- Team (typically on this call)
  - Jim McCullers (present)
ASCENT PACSAT

---
  - Develop deployable solar panels
  - Vincent Risalvato
  - Duane Moberg (present)
  - Design solar panel and hinge solution
    - Result is a model of solar panels and hinges that fit in the pockets of the currently envisioned 3U structure.
    - Are we ready to prototype real hardware? Any luck getting cells?
    - If things are going to plan, we had a meeting with Mark Kanawati earlier today.
ASCENT Deployable Solar Panels

---
  - Identify AX5043 Replacement
  - Identify LNA Replacement
  - Dave Hartrum (present)
ASCENT RF Chip Trade Study

---
  - Identify environmental sensor for CubeSat Simulator use by Frank Karnauskas network
  - Joseph DiVerdi (present)
ASCENT Environmental Sensors